## All
ID | Backlog | Subtask | Sprint | Start Date | End Date
1 | Project Setup | complete pop draft | 1 | 2025-05-10 | 2025-05-18
2 | Project Setup | complete user-stories draft | 1 | 2025-05-10 | 2025-05-18
3 | Project Setup | complete design requirements draft | 1 | 2025-05-10 | 2025-05-18
4 | Project Setup | complete mvs draft | 1 | 2025-05-10 | 2025-05-18
5 | Project Setup | complete sdp draft | 1 | 2025-05-10 | 2025-05-18
6 | Project Setup | setup and launch basic react application | 1 | 2025-05-10 | 2025-05-18
7 | Project Setup | install and setup tailwind css | 1 | 2025-05-10 | 2025-05-18
8 | Project Setup | install and setup ui/shadcn | 1 | 2025-05-10 | 2025-05-18
9 | Intro to Solo-scrum | Define definition of done for all backlog items in sprint 1 | 2 | 2025-05-10 | 2025-05-18
10 | Intro to Solo-scrum | Define goal for sprint 1 | 2 | 2025-05-10 | 2025-05-18
11 | Intro to Solo-scrum | Complete first standup with Mom + Dad, documenting things on Notion | 2 | 2025-05-10 | 2025-05-18
12 | Intro to Solo-scrum | Complete and document all standups in first sprint | 2 | 2025-05-10 | 2025-05-18
13 | Intro to Solo-scrum | Complete first retrospective with parents | 2 | 2025-05-10 | 2025-05-18
14 | Intro to Solo-scrum | Format and upload the following to github for the first sprint: standups, retrospective, backlog items and descriptions, sprint goal, definition of done | 2 | 2025-05-10 | 2025-05-18
15 | Intro to Solo-scrum | Create sprint 1 review presentation | 2 | 2025-05-10 | 2025-05-18
16 | Intro to Solo-scrum | Give presentation to parents (and Dr. Raymer if possible) | 2 | 2025-05-10 | 2025-05-19
17 | Intro to Solo-scrum | Create timeline and gantt chart | 2 | 2025-05-10 | 2025-05-24
18 | Intro to Solo-scrum | Complete major sprint feedback for sprint 1 in sprint dashboard in Notion | 2 | 2025-05-10 | 2025-05-18
19 | UI/UX Foundation | Read intro to React article https://www.freecodecamp.org/news/learn-react-key-concepts/ | 2 | 2025-05-10 | 2025-05-18
20 | UI/UX Foundation | Create 2 quizzes | 2 | 2025-05-10 | 2025-05-18
21 | UI/UX Foundation | Take the first, easier quiz and grade it | 2 | 2025-05-10 | 2025-05-18
22 | UI/UX Foundation | Create wireframe of first web page | 2 | 2025-05-10 | 2025-05-18
23 | UI/UX Foundation | Create figma mockup of first page using styling capable with shadcn/ui and tailwind css | 2 | 2025-05-10 | 2025-05-18
24 | UI/UX Foundation | Complete 2nd, more difficult quiz | 2 | 2025-05-10 | 2025-05-19
25 | UI/UX Foundation | Add UI/UX related slides to powerpoint (first sprint presentation) | 2 | 2025-05-10 | 2025-05-18
26 | UI/UX Foundation | Populate web app with static components (table, stat cards, plan summary, submit button) | 2 | 2025-05-21 | 2025-05-22
27 | Data Entry Table | Develop button feature that adds an additional page ideally at the bottom of the data table | 2
28 | Data Entry Table | Add update functionality that allows the user to click individual cells and modify their contents | 2
29 | Data Entry Table | Add calendar selection option for start date and end date columns | 2
30 | Data Entry Table | Implement numeric column that restricts user inputs to solely positive numbers | 2
31 | Data Entry Table | Implement dropdown selection menu for the categories column | 2
32 | Data Entry Table | Load in selectable categories and their colors from a text file | 2
33 | Data Entry Table | Add time sum feature that sums and displays all values from the "# Estimate" column below the last entry of the column | 2
34 | Data Entry Table | Add delete feature that allows the user to easily delete rows by selecting them with their mouse | 2
35 | Data Entry Table | Write unit tests to ensure functionality | 2
36
37 | Settings Toggle |  | 3
38
39
40
41
42
| Notion API Integration |  | 3
| Database Setup & Integration |  | 3
| Backend Setup |  | 4
| Stat Card System |  | 4
| Feedback System |  | 4
| Time Estimation Autofill |  | 5
| Task Duration Prediction Model |  | 5

## Rough
ID | Backlog | Sprint | Start Date | End Date | Duration
1 | Project Setup | Sprint 1 | 2025-05-10 | 2025-05-18 | 8
2 | Intro to Solo-scrum | Sprint 2 | 2025-05-10 | 2025-05-20 | 10
3 | UI/UX Foundation | Sprint 3 | 2025-05-10 | 2025-06-01 | 22
4 | Intro to React | Sprint 3 | 2025-05-23 | 2025-05-30 | 7
5 | Data Entry Table | Sprint 3 | 2025-06-01 | 2025-06-10 | 9
6 | Documentation Catchup |  | 2025-06-09 | 2025-06-11 | 2
7 | Retro3: Reward System 2.0 |  | 2025-06-11 | 2025-06-16 | 5
8 | Intro to Code Reviews & Testing |  | 2025-06-12 | 2025-06-16 | 4
9 | Stat Card System |  | 2025-06-16 | 2025-06-21 | 5
10 | Feedback System |  | 2025-06-21 | 2025-06-25 | 4
11 | Database Setup & Integration |  | 2025-06-25 | 2025-06-28 | 3
12 | Backend Setup |  | 2025-06-28 | 2025-07-02 | 4
13 | Notion API Integration |  | 2025-07-02 | 2025-07-04 | 2
14 | Time Estimation Autofill |  | 2025-07-04 | 2025-07-06 | 2

## Sprint 3
Sprint | Backlog Item | Subtask | Start_Date | End_Date | Duration
3 | Intro to React | React Styles - Project | 2025-05-29 | 2025-05-30 | 1
3 | Intro to React | React Styles - Quiz | 2025-05-29 | 2025-05-30 | 1
3 | Intro to React | React Forms - Lesson | 2025-05-30 | 2025-05-31 | 1
3 | Intro to React | React Forms - Article | 2025-05-30 | 2025-05-31 | 1
3 | Intro to React | React Forms - Project | 2025-05-30 | 2025-05-31 | 1
3 | Intro to React | React Forms - Quiz | 2025-05-30 | 2025-05-31 | 1
3 | UI/UX Foundation | Second React Quiz | 2025-05-31 | 2025-06-01 | 1
3 | UI/UX Foundation | Third React Quiz | 2025-05-31 | 2025-06-01 | 1
3 | Data Entry Table | Calendar popup | 2025-06-01 | 2025-06-02 | 1
3 | Data Entry Table | Numeric column w restrictions | 2025-06-01 | 2025-06-02 | 1
3 | Data Entry Table | Category dropdown menu | 2025-06-01 | 2025-06-02 | 1
3 | Data Entry Table | Load categories from txt | 2025-06-02 | 2025-06-03 | 1
3 | Data Entry Table | Time sum | 2025-06-02 | 2025-06-03 | 1
3 | Data Entry Table | Additional page button | 2025-06-03 | 2025-06-04 | 1
3 | Data Entry Table | Cell clickability | 2025-06-04 | 2025-06-05 | 1
3 | Data Entry Table | Delete row | 2025-06-04 | 2025-06-05 | 1
3 | Data Entry Table | Write unit tests | 2025-06-05 | 2025-06-06 | 1

## Sprint 4
Sprint | Backlog Item | Subtask | Start_Date | End_Date | Duration | Notes
4 | Documentation Catchup | Create sprint 4 timeline | 2025-06-12 | 2025-06-13 | 1 | List out the specific tasks for all assigned backlog items, estimate how long, and when it will start/end, then create a graph to visually see the plan, then add to the standup presentation and assets folder for this sprint
4 | Documentation Catchup | Update mvs | 2025-06-12 | 2025-06-13 | 1 | Add specific requirements to the MVS to make it more clear when the project will be considered finished
4 | Retro3: Reward System 2.0 | Write up new plan document | 2025-06-12 | 2025-06-13 | 1 | Write up new plan discussed in retrospective #3
4 | Retro3: Reward System 2.0 | Design templates | 2025-06-12 | 2025-06-13 | 1 | Pull request, sprint, backlog, retrospective, daily standup
4 | Retro3: Reward System 2.0 | Implement plan | 2025-06-13 | 2025-06-21 | 8 | Follow the plan everyday, filling out the corresponding section for the day in the document. Then at the end evaluate, if reward qualifications were met.
4 | Retro3: Reward System 2.0 | Upload plan results page | 2025-06-21 | 2025-06-22 | 1 | Scan last page where I document my progress and performance
4 | Intro to Code Reviews & Testing | Setup | 2025-06-12 | 2025-06-13 | 1 | Create a new branch for the datatable, delete the testing files on main, update remote GitHub repository
4 | Intro to Code Reviews & Testing | Research Vitest + React testing-library | 2025-06-13 | 2025-06-14 | 1 | Gain a better understanding of how to write tests using these libraries
4 | Intro to Code Reviews & Testing | Unit Testing | 2025-06-13 | 2025-06-15 | 2 | Write unit tests for each component of the datatable, run the tests, modify code until all cases pass
4 | Intro to Code Reviews & Testing | Integration testing | 2025-06-14 | 2025-06-15 | 1 | Write and implement integration tests made between different subcomponents of the data table
4 | Intro to Code Reviews & Testing | Pull Request | 2025-06-15 | 2025-06-16 | 1 | Create a pull request on GitHub including summary and scope
4 | Intro to Code Reviews & Testing | Leave comments | 2025-06-15 | 2025-06-16 | 1 | Leave self-review comments simulating feedback, also feel free to leverage ChatGPT here for more detailed feedback
4 | Intro to Code Reviews & Testing | Update code | 2025-06-16 | 2025-06-18 | 2 | Based on the self-review comments, make the appropriate changes to the code, ensuring things work before moving on
4 | Intro to Code Reviews & Testing | Changes documentation | 2025-06-18 | 2025-06-19 | 1 | Write up documentation detailing the original code, the feedback, the change, why the old example is bad, and why the new code is good
4 | Intro to Code Reviews & Testing | Merge with main | 2025-06-19 | 2025-06-20 | 1 | Merge the pull request with main, handle any merge conflicts here
4 | Stat Card System | Setup |  |  |  | Create new branch, setup test data, create master container for system
4 | Stat Card System | Build the react component |  |  |  | Includes the following info: Day of the week + date (e.g., Monday 6/9), Current plan's time sum, Average time, Standard deviation, Status (e.g., Good, Moderate, Poor)
4 | Stat Card System | Add default state for component |  |  |  | If a day has no relevant data to display, ensure it displays something and no calculations are called causing errors, also ensure it has some default color (like grey or something)
4 | Stat Card System | Dynamic coloring |  |  |  | Ensure stat cards change color based on the current state of data entered in the table, the color changes are responsive and update with changes in the data table or from data on the backend
4 | Stat Card System | Status count feature |  |  |  | Area at bottom of container that shows the count for each status type ( ie good: x3, moderate: x2, poor: x2)
4 | Stat Card System | Pull request |  |  |  | Initiate pull request and document important details, use the template
4 | Stat Card System | Testing |  |  |  | Write and perform unit tests + integration tests, ensure all test cases pass before moving on
4 | Stat Card System | Self-review comments |  |  |  | Write comments on code simulating feedback, feel free to use ChatGPT in collaboriation with self written comments
4 | Stat Card System | Apply code changes |  |  |  | Based on the feedback, make updates to the code
4 | Stat Card System | Document changes |  |  |  | Document the changes that were made, why the change was made, etc
4 | Stat Card System | Final code review and publishing |  |  |  | Perform a final review, then merge with main
Legend
Reward System 2.0
Documentation Catchup
Code Review &Testing

## Sheet2
Backlog Item | Subtask | Start_Date | Duration
Documentation Catchup | Create sprint 4 timeline | 45820 | 1
Documentation Catchup | Update mvs | 45820 | 1
Retro3: Reward System 2.0 | Write up new plan document | 45820 | 1
Retro3: Reward System 2.0 | Design templates | 45820 | 1
Retro3: Reward System 2.0 | Implement plan | 45821 | 8
Retro3: Reward System 2.0 | Upload plan results page | 45829 | 1
Intro to Code Reviews & Testing | Setup | 45820 | 1
Intro to Code Reviews & Testing | Research Vitest + React testing-library | 45821 | 1
Intro to Code Reviews & Testing | Unit Testing | 45821 | 2
Intro to Code Reviews & Testing | Integration testing | 45822 | 1
Intro to Code Reviews & Testing | Pull Request | 45823 | 1
Intro to Code Reviews & Testing | Leave comments | 45823 | 1
Intro to Code Reviews & Testing | Update code | 45824 | 2
Intro to Code Reviews & Testing | Changes documentation | 45826 | 1
Intro to Code Reviews & Testing | Merge with main | 45827 | 1

## (Old) Sprint2-3
Sprint | Backlog Item | Subtask | Start_Date | End_Date | Duration
Sprint 2 | Intro to Solo-scrum | Edit SDP: detailed timeline for sprints 2 & 3 | 2025-05-20 | 2025-05-20 | 1
Sprint 2 | UI/UX Foundation | Populate web app with static components | 2025-05-21 | 2025-05-22 | 2
Sprint 2 | UI/UX Foundation | Complete 2nd, more difficult quiz with 75% or greater | 2025-05-23 | 2025-05-24 | 2
Sprint 2 | Data Entry Table | Add button to append new page to table | 2025-05-21 | 2025-05-21 | 1
Sprint 2 | Data Entry Table | Enable cell-click updates | 2025-05-21 | 2025-05-22 | 2
Sprint 2 | Data Entry Table | Add calendar for start/end date columns | 2025-05-22 | 2025-05-22 | 1
Sprint 2 | Data Entry Table | Restrict numeric column to positive inputs | 2025-05-22 | 2025-05-23 | 2
Sprint 2 | Data Entry Table | Implement dropdown for categories | 2025-05-23 | 2025-05-23 | 1
Sprint 2 | Data Entry Table | Load category names/colors from text file | 2025-05-23 | 2025-05-23 | 1
Sprint 2 | Data Entry Table | Add time summation feature | 2025-05-24 | 2025-05-24 | 1
Sprint 2 | Data Entry Table | Add row deletion feature via mouse selection | 2025-05-24 | 2025-05-24 | 1
Sprint 2 | Data Entry Table | Write unit tests | 2025-05-24 | 2025-05-24 | 1
Sprint 3 | Database Setup & Integration | Audit and inventory raw data | 2025-05-26 | 2025-05-26 | 1
Sprint 3 | Database Setup & Integration | Define cleaning and privacy rules | 2025-05-26 | 2025-05-27 | 2
Sprint 3 | Database Setup & Integration | Clean and preprocess data | 2025-05-27 | 2025-05-28 | 2
Sprint 3 | Database Setup & Integration | Design MongoDB schema | 2025-05-28 | 2025-05-28 | 1
Sprint 3 | Database Setup & Integration | Set up MongoDB Atlas cluster | 2025-05-28 | 2025-05-29 | 2
Sprint 3 | Database Setup & Integration | Insert cleaned data | 2025-05-29 | 2025-05-29 | 1
Sprint 3 | Database Setup & Integration | Create indexes for common queries | 2025-05-30 | 2025-05-30 | 1
Sprint 3 | Database Setup & Integration | Write connection instructions for backend | 2025-05-30 | 2025-05-30 | 1
Sprint 3 | Database Setup & Integration | Test access and security | 2025-05-31 | 2025-05-31 | 1
Sprint 3 | Backend Setup | Initialize Flask project structure | 2025-05-26 | 2025-05-26 | 1
Sprint 3 | Backend Setup | Install core dependencies | 2025-05-26 | 2025-05-26 | 1
Sprint 3 | Backend Setup | Load and use environment variables | 2025-05-27 | 2025-05-27 | 1
Sprint 3 | Backend Setup | Connect to MongoDB Atlas | 2025-05-27 | 2025-05-28 | 2
Sprint 3 | Backend Setup | Create CRUD API endpoints | 2025-05-28 | 2025-05-29 | 2
Sprint 3 | Backend Setup | Define data access layer (DAL) | 2025-05-29 | 2025-05-29 | 1
Sprint 3 | Backend Setup | Implement input validation and error handling | 2025-05-30 | 2025-05-30 | 1
Sprint 3 | Backend Setup | Write unit and integration tests | 2025-05-30 | 2025-05-31 | 2
Sprint 3 | Backend Setup | Document the API | 2025-05-31 | 2025-05-31 | 1
Sprint 3 | Backend Setup | Run end-to-end tests w/ live DB | 2025-05-31 | 2025-05-31 | 1