## Rough
ID | Backlog | Sprint | Start Date | End Date | Duration
1 | Project Setup | Sprint 1 | 2025-05-10 | 2025-05-18 | 8
2 | Intro to Solo-scrum | Sprint 2 | 2025-05-10 | 2025-05-20 | 10
3 | UI/UX Foundation | Sprint 3 | 2025-05-10 | 2025-06-01 | 22
4 | Intro to React | Sprint 3 | 2025-05-23 | 2025-05-30 | 7
5 | Data Entry Table | Sprint 3 | 2025-06-01 | 2025-06-10 | 9
6 | Documentation Catchup |  | 2025-06-09 | 2025-06-11 | 2
7 | Retro3: Reward System 2.0 |  | 2025-06-11 | 2025-06-16 | 5
8 | Intro to Code Reviews & Testing |  | 2025-06-12 | 2025-06-16 | 4
9 | Stat Card System |  | 2025-06-16 | 2025-06-23 | 7
10 | Database Setup & Integration |  | 2025-06-24 | 2025-07-01 | 7
11 | Backend Setup |  | 2025-06-24 | 2025-07-01 | 7
12 | Feedback System |  | 2025-07-01 | 2025-07-07 | 6
13 | Notion API Integration |  | 2025-07-07 | 2025-07-10 | 3
14 | Time Estimation Autofill |  | 2025-07-10 | 2025-07-14 | 4
Sprint 6
6/24-29
Today
6/28

## Aaa
ID | Backlog | Sprint | Start Date | End Date | Duration
1 | Project Setup |  | 2025-05-10 | 2025-05-18 | 8
2 | Intro to Solo-scrum |  | 2025-05-10 | 2025-05-20 | 10
3 | UI/UX Foundation |  | 2025-05-10 | 2025-06-01 | 22
4 | Intro to React |  | 2025-05-23 | 2025-05-30 | 7
5 | Data Entry Table |  | 2025-06-01 | 2025-06-10 | 9
6 | Documentation Catchup |  | 2025-06-09 | 2025-06-11 | 2
7 | Retro3: Reward System 2.0 |  | 2025-06-11 | 2025-06-16 | 5
8 | Intro to Code Reviews & Testing |  | 2025-06-12 | 2025-06-16 | 4
9 | Stat Card System |  | 2025-06-16 | 2025-06-23 | 7
10 | Database Setup p1 |  | 2025-06-24 | 2025-07-01 | 7
11 | Database Setup p2 |  | 2025-08-19 | 2025-08-26 | 7
12 | Backend Setup p1 |  | 2025-06-24 | 2025-07-01 | 7
13 | Backend Setup p2 |  | 2025-08-19 | 2025-08-26 | 7
14 | Intro to Flask |  | 2025-08-19 | 2025-08-26 | 7
15 | Frontend & Backend Integration |  | 2025-09-01 | 2025-09-06 | 5
16 | Feedback System |  | 2025-09-08 | 2025-09-13 | 5
17 | Notion API Integration |  | 2025-09-08 | 2025-09-13 | 5
18 | End-to-End Testing |  | 2025-09-15 | 2025-09-20 | 5
19 | Performance Testing |  | 2025-09-15 | 2025-09-20 | 5
20 | Presentation Readiness |  | 2025-09-22 | 2025-09-27 | 5
ID | Backlog | Start Date | End Date | Duration
11 | Database Setup | 2025-08-19 | 2025-08-26 | 7
13 | Backend Setup | 2025-08-19 | 2025-08-26 | 7
14 | Intro to Flask | 2025-08-19 | 2025-08-26 | 7
15 | Frontend & Backend Integration | 2025-09-01 | 2025-09-06 | 5
16 | Feedback System | 2025-09-08 | 2025-09-13 | 5
17 | Notion API Integration | 2025-09-08 | 2025-09-13 | 5
18 | End-to-End Testing | 2025-09-15 | 2025-09-20 | 5
19 | Performance Testing | 2025-09-15 | 2025-09-20 | 5
20 | Presentation Readiness | 2025-09-22 | 2025-09-27 | 5

## Sprint 3
Sprint | Backlog Item | Subtask | Start_Date | End_Date | Duration
3 | Intro to React | React Styles - Project | 2025-05-29 | 2025-05-30 | 1
3 | Intro to React | React Styles - Quiz | 2025-05-29 | 2025-05-30 | 1
3 | Intro to React | React Forms - Lesson | 2025-05-30 | 2025-05-31 | 1
3 | Intro to React | React Forms - Article | 2025-05-30 | 2025-05-31 | 1
3 | Intro to React | React Forms - Project | 2025-05-30 | 2025-05-31 | 1
3 | Intro to React | React Forms - Quiz | 2025-05-30 | 2025-05-31 | 1
3 | UI/UX Foundation | Second React Quiz | 2025-05-31 | 2025-06-01 | 1
3 | UI/UX Foundation | Third React Quiz | 2025-05-31 | 2025-06-01 | 1
3 | Data Entry Table | Calendar popup | 2025-06-01 | 2025-06-02 | 1
3 | Data Entry Table | Numeric column w restrictions | 2025-06-01 | 2025-06-02 | 1
3 | Data Entry Table | Category dropdown menu | 2025-06-01 | 2025-06-02 | 1
3 | Data Entry Table | Load categories from txt | 2025-06-02 | 2025-06-03 | 1
3 | Data Entry Table | Time sum | 2025-06-02 | 2025-06-03 | 1
3 | Data Entry Table | Additional page button | 2025-06-03 | 2025-06-04 | 1
3 | Data Entry Table | Cell clickability | 2025-06-04 | 2025-06-05 | 1
3 | Data Entry Table | Delete row | 2025-06-04 | 2025-06-05 | 1
3 | Data Entry Table | Write unit tests | 2025-06-05 | 2025-06-06 | 1

## Sprint 4
Sprint | Backlog Item | Subtask | Start_Date | End_Date | Duration | Notes
4 | Documentation Catchup | Create sprint 4 timeline | 2025-06-12 | 2025-06-13 | 1 | List out the specific tasks for all assigned backlog items, estimate how long, and when it will start/end, then create a graph to visually see the plan, then add to the standup presentation and assets folder for this sprint
4 | Documentation Catchup | Update mvs | 2025-06-12 | 2025-06-13 | 1 | Add specific requirements to the MVS to make it more clear when the project will be considered finished
4 | Retro3: Reward System 2.0 | Write up new plan document | 2025-06-12 | 2025-06-13 | 1 | Write up new plan discussed in retrospective #3
4 | Retro3: Reward System 2.0 | Design templates | 2025-06-12 | 2025-06-13 | 1 | Pull request, sprint, backlog, retrospective, daily standup
4 | Retro3: Reward System 2.0 | Implement plan | 2025-06-13 | 2025-06-21 | 8 | Follow the plan everyday, filling out the corresponding section for the day in the document. Then at the end evaluate, if reward qualifications were met.
4 | Retro3: Reward System 2.0 | Upload plan results page | 2025-06-21 | 2025-06-22 | 1 | Scan last page where I document my progress and performance
4 | Intro to Code Reviews & Testing | Setup | 2025-06-12 | 2025-06-13 | 1 | Create a new branch for the datatable, delete the testing files on main, update remote GitHub repository
4 | Intro to Code Reviews & Testing | Research Vitest + React testing-library | 2025-06-13 | 2025-06-14 | 1 | Gain a better understanding of how to write tests using these libraries
4 | Intro to Code Reviews & Testing | Unit Testing | 2025-06-13 | 2025-06-15 | 2 | Write unit tests for each component of the datatable, run the tests, modify code until all cases pass
4 | Intro to Code Reviews & Testing | Integration testing | 2025-06-14 | 2025-06-15 | 1 | Write and implement integration tests made between different subcomponents of the data table
4 | Intro to Code Reviews & Testing | Pull Request | 2025-06-15 | 2025-06-16 | 1 | Create a pull request on GitHub including summary and scope
4 | Intro to Code Reviews & Testing | Leave comments | 2025-06-15 | 2025-06-16 | 1 | Leave self-review comments simulating feedback, also feel free to leverage ChatGPT here for more detailed feedback
4 | Intro to Code Reviews & Testing | Update code | 2025-06-16 | 2025-06-18 | 2 | Based on the self-review comments, make the appropriate changes to the code, ensuring things work before moving on
4 | Intro to Code Reviews & Testing | Changes documentation | 2025-06-18 | 2025-06-19 | 1 | Write up documentation detailing the original code, the feedback, the change, why the old example is bad, and why the new code is good
4 | Intro to Code Reviews & Testing | Merge with main | 2025-06-19 | 2025-06-20 | 1 | Merge the pull request with main, handle any merge conflicts here
4 | Stat Card System | Setup |  |  |  | Create new branch, setup test data, create master container for system
4 | Stat Card System | Build the react component |  |  |  | Includes the following info: Day of the week + date (e.g., Monday 6/9), Current plan's time sum, Average time, Standard deviation, Status (e.g., Good, Moderate, Poor)
4 | Stat Card System | Add default state for component |  |  |  | If a day has no relevant data to display, ensure it displays something and no calculations are called causing errors, also ensure it has some default color (like grey or something)
4 | Stat Card System | Dynamic coloring |  |  |  | Ensure stat cards change color based on the current state of data entered in the table, the color changes are responsive and update with changes in the data table or from data on the backend
4 | Stat Card System | Status count feature |  |  |  | Area at bottom of container that shows the count for each status type ( ie good: x3, moderate: x2, poor: x2)
4 | Stat Card System | Pull request |  |  |  | Initiate pull request and document important details, use the template
4 | Stat Card System | Testing |  |  |  | Write and perform unit tests + integration tests, ensure all test cases pass before moving on
4 | Stat Card System | Self-review comments |  |  |  | Write comments on code simulating feedback, feel free to use ChatGPT in collaboriation with self written comments
4 | Stat Card System | Apply code changes |  |  |  | Based on the feedback, make updates to the code
4 | Stat Card System | Document changes |  |  |  | Document the changes that were made, why the change was made, etc
4 | Stat Card System | Final code review and publishing |  |  |  | Perform a final review, then merge with main
Legend
Reward System 2.0
Documentation Catchup
Code Review &Testing

## (Old) Sprint2-3
Sprint | Backlog Item | Subtask | Start_Date | End_Date | Duration
Sprint 2 | Intro to Solo-scrum | Edit SDP: detailed timeline for sprints 2 & 3 | 2025-05-20 | 2025-05-20 | 1
Sprint 2 | UI/UX Foundation | Populate web app with static components | 2025-05-21 | 2025-05-22 | 2
Sprint 2 | UI/UX Foundation | Complete 2nd, more difficult quiz with 75% or greater | 2025-05-23 | 2025-05-24 | 2
Sprint 2 | Data Entry Table | Add button to append new page to table | 2025-05-21 | 2025-05-21 | 1
Sprint 2 | Data Entry Table | Enable cell-click updates | 2025-05-21 | 2025-05-22 | 2
Sprint 2 | Data Entry Table | Add calendar for start/end date columns | 2025-05-22 | 2025-05-22 | 1
Sprint 2 | Data Entry Table | Restrict numeric column to positive inputs | 2025-05-22 | 2025-05-23 | 2
Sprint 2 | Data Entry Table | Implement dropdown for categories | 2025-05-23 | 2025-05-23 | 1
Sprint 2 | Data Entry Table | Load category names/colors from text file | 2025-05-23 | 2025-05-23 | 1
Sprint 2 | Data Entry Table | Add time summation feature | 2025-05-24 | 2025-05-24 | 1
Sprint 2 | Data Entry Table | Add row deletion feature via mouse selection | 2025-05-24 | 2025-05-24 | 1
Sprint 2 | Data Entry Table | Write unit tests | 2025-05-24 | 2025-05-24 | 1
Sprint 3 | Database Setup & Integration | Audit and inventory raw data | 2025-05-26 | 2025-05-26 | 1
Sprint 3 | Database Setup & Integration | Define cleaning and privacy rules | 2025-05-26 | 2025-05-27 | 2
Sprint 3 | Database Setup & Integration | Clean and preprocess data | 2025-05-27 | 2025-05-28 | 2
Sprint 3 | Database Setup & Integration | Design MongoDB schema | 2025-05-28 | 2025-05-28 | 1
Sprint 3 | Database Setup & Integration | Set up MongoDB Atlas cluster | 2025-05-28 | 2025-05-29 | 2
Sprint 3 | Database Setup & Integration | Insert cleaned data | 2025-05-29 | 2025-05-29 | 1
Sprint 3 | Database Setup & Integration | Create indexes for common queries | 2025-05-30 | 2025-05-30 | 1
Sprint 3 | Database Setup & Integration | Write connection instructions for backend | 2025-05-30 | 2025-05-30 | 1
Sprint 3 | Database Setup & Integration | Test access and security | 2025-05-31 | 2025-05-31 | 1
Sprint 3 | Backend Setup | Initialize Flask project structure | 2025-05-26 | 2025-05-26 | 1
Sprint 3 | Backend Setup | Install core dependencies | 2025-05-26 | 2025-05-26 | 1
Sprint 3 | Backend Setup | Load and use environment variables | 2025-05-27 | 2025-05-27 | 1
Sprint 3 | Backend Setup | Connect to MongoDB Atlas | 2025-05-27 | 2025-05-28 | 2
Sprint 3 | Backend Setup | Create CRUD API endpoints | 2025-05-28 | 2025-05-29 | 2
Sprint 3 | Backend Setup | Define data access layer (DAL) | 2025-05-29 | 2025-05-29 | 1
Sprint 3 | Backend Setup | Implement input validation and error handling | 2025-05-30 | 2025-05-30 | 1
Sprint 3 | Backend Setup | Write unit and integration tests | 2025-05-30 | 2025-05-31 | 2
Sprint 3 | Backend Setup | Document the API | 2025-05-31 | 2025-05-31 | 1
Sprint 3 | Backend Setup | Run end-to-end tests w/ live DB | 2025-05-31 | 2025-05-31 | 1