## All
ID | Backlog | Subtask | Sprint | Start Date | End Date
1 | Project Setup | complete pop draft | 1 | 2025-05-10 | 2025-05-18
2 | Project Setup | complete user-stories draft | 1 | 2025-05-10 | 2025-05-18
3 | Project Setup | complete design requirements draft | 1 | 2025-05-10 | 2025-05-18
4 | Project Setup | complete mvs draft | 1 | 2025-05-10 | 2025-05-18
5 | Project Setup | complete sdp draft | 1 | 2025-05-10 | 2025-05-18
6 | Project Setup | setup and launch basic react application | 1 | 2025-05-10 | 2025-05-18
7 | Project Setup | install and setup tailwind css | 1 | 2025-05-10 | 2025-05-18
8 | Project Setup | install and setup ui/shadcn | 1 | 2025-05-10 | 2025-05-18
9 | Intro to Solo-scrum | Define definition of done for all backlog items in sprint 1 | 2 | 2025-05-10 | 2025-05-18
10 | Intro to Solo-scrum | Define goal for sprint 1 | 2 | 2025-05-10 | 2025-05-18
11 | Intro to Solo-scrum | Complete first standup with Mom + Dad, documenting things on Notion | 2 | 2025-05-10 | 2025-05-18
12 | Intro to Solo-scrum | Complete and document all standups in first sprint | 2 | 2025-05-10 | 2025-05-18
13 | Intro to Solo-scrum | Complete first retrospective with parents | 2 | 2025-05-10 | 2025-05-18
14 | Intro to Solo-scrum | Format and upload the following to github for the first sprint: standups, retrospective, backlog items and descriptions, sprint goal, definition of done | 2 | 2025-05-10 | 2025-05-18
15 | Intro to Solo-scrum | Create sprint 1 review presentation | 2 | 2025-05-10 | 2025-05-18
16 | Intro to Solo-scrum | Give presentation to parents (and Dr. Raymer if possible) | 2 | 2025-05-10 | 2025-05-19
17 | Intro to Solo-scrum | Create timeline and gantt chart | 2 | 2025-05-10 | 2025-05-24
18 | Intro to Solo-scrum | Complete major sprint feedback for sprint 1 in sprint dashboard in Notion | 2 | 2025-05-10 | 2025-05-18
19 | UI/UX Foundation | Read intro to React article https://www.freecodecamp.org/news/learn-react-key-concepts/ | 2 | 2025-05-10 | 2025-05-18
20 | UI/UX Foundation | Create 2 quizzes | 2 | 2025-05-10 | 2025-05-18
21 | UI/UX Foundation | Take the first, easier quiz and grade it | 2 | 2025-05-10 | 2025-05-18
22 | UI/UX Foundation | Create wireframe of first web page | 2 | 2025-05-10 | 2025-05-18
23 | UI/UX Foundation | Create figma mockup of first page using styling capable with shadcn/ui and tailwind css | 2 | 2025-05-10 | 2025-05-18
24 | UI/UX Foundation | Complete 2nd, more difficult quiz | 2 | 2025-05-10 | 2025-05-19
25 | UI/UX Foundation | Add UI/UX related slides to powerpoint (first sprint presentation) | 2 | 2025-05-10 | 2025-05-18
26 | UI/UX Foundation | Populate web app with static components (table, stat cards, plan summary, submit button) | 2 | 2025-05-21 | 2025-05-22
27 | Data Entry Table | Develop button feature that adds an additional page ideally at the bottom of the data table | 2
28 | Data Entry Table | Add update functionality that allows the user to click individual cells and modify their contents | 2
29 | Data Entry Table | Add calendar selection option for start date and end date columns | 2
30 | Data Entry Table | Implement numeric column that restricts user inputs to solely positive numbers | 2
31 | Data Entry Table | Implement dropdown selection menu for the categories column | 2
32 | Data Entry Table | Load in selectable categories and their colors from a text file | 2
33 | Data Entry Table | Add time sum feature that sums and displays all values from the "# Estimate" column below the last entry of the column | 2
34 | Data Entry Table | Add delete feature that allows the user to easily delete rows by selecting them with their mouse | 2
35 | Data Entry Table | Write unit tests to ensure functionality | 2
36
37 | Settings Toggle |  | 3
38
39
40
41
42
| Notion API Integration |  | 3
| Database Setup & Integration |  | 3
| Backend Setup |  | 4
| Stat Card System |  | 4
| Feedback System |  | 4
| Time Estimation Autofill |  | 5
| Task Duration Prediction Model |  | 5

## Rough
ID | Backlog | Sprint | Start Date | End Date | Duration
1 | Project Setup | Sprint 1 | 2025-05-10 | 2025-05-18 | 8
2 | Intro to Solo-scrum | Sprint 2 | 2025-05-10 | 2025-05-20 | 10
3 | UI/UX Foundation | Sprint 3 | 2025-05-10 | 2025-06-01 | 22
4 | Intro to React | Sprint 3 | 2025-05-23 | 2025-05-30 | 7
5 | Data Entry Table | Sprint 3 | 2025-06-01 | 2025-06-10 | 9
6 | Database Setup & Integration |  | 2025-06-09 | 2025-06-12 | 3
7 | Backend Setup |  | 2025-06-12 | 2025-06-19 | 7
8 | Stat Card System |  | 2025-06-19 | 2025-06-21 | 2
9 | Notion API Integration |  | 2025-06-21 | 2025-06-24 | 3
10 | Feedback System |  | 2025-06-24 | 2025-06-30 | 6
11 | Time Estimation Autofill |  | 2025-06-30 | 2025-07-03 | 3

## Sprint 3
Sprint | Backlog Item | Subtask | Start_Date | End_Date | Duration
3 | Intro to React | React Styles - Project | 2025-05-29 | 2025-05-30 | 1
3 | Intro to React | React Styles - Quiz | 2025-05-29 | 2025-05-30 | 1
3 | Intro to React | React Forms - Lesson | 2025-05-30 | 2025-05-31 | 1
3 | Intro to React | React Forms - Article | 2025-05-30 | 2025-05-31 | 1
3 | Intro to React | React Forms - Project | 2025-05-30 | 2025-05-31 | 1
3 | Intro to React | React Forms - Quiz | 2025-05-30 | 2025-05-31 | 1
3 | UI/UX Foundation | Second React Quiz | 2025-05-31 | 2025-06-01 | 1
3 | UI/UX Foundation | Third React Quiz | 2025-05-31 | 2025-06-01 | 1
3 | Data Entry Table | Calendar popup | 2025-06-01 | 2025-06-02 | 1
3 | Data Entry Table | Numeric column w restrictions | 2025-06-01 | 2025-06-02 | 1
3 | Data Entry Table | Category dropdown menu | 2025-06-01 | 2025-06-02 | 1
3 | Data Entry Table | Load categories from txt | 2025-06-02 | 2025-06-03 | 1
3 | Data Entry Table | Time sum | 2025-06-02 | 2025-06-03 | 1
3 | Data Entry Table | Additional page button | 2025-06-03 | 2025-06-04 | 1
3 | Data Entry Table | Cell clickability | 2025-06-04 | 2025-06-05 | 1
3 | Data Entry Table | Delete row | 2025-06-04 | 2025-06-05 | 1
3 | Data Entry Table | Write unit tests | 2025-06-05 | 2025-06-06 | 1

## (Old) Sprint2-3
Sprint | Backlog Item | Subtask | Start_Date | End_Date | Duration
Sprint 2 | Intro to Solo-scrum | Edit SDP: detailed timeline for sprints 2 & 3 | 2025-05-20 | 2025-05-20 | 1
Sprint 2 | UI/UX Foundation | Populate web app with static components | 2025-05-21 | 2025-05-22 | 2
Sprint 2 | UI/UX Foundation | Complete 2nd, more difficult quiz with 75% or greater | 2025-05-23 | 2025-05-24 | 2
Sprint 2 | Data Entry Table | Add button to append new page to table | 2025-05-21 | 2025-05-21 | 1
Sprint 2 | Data Entry Table | Enable cell-click updates | 2025-05-21 | 2025-05-22 | 2
Sprint 2 | Data Entry Table | Add calendar for start/end date columns | 2025-05-22 | 2025-05-22 | 1
Sprint 2 | Data Entry Table | Restrict numeric column to positive inputs | 2025-05-22 | 2025-05-23 | 2
Sprint 2 | Data Entry Table | Implement dropdown for categories | 2025-05-23 | 2025-05-23 | 1
Sprint 2 | Data Entry Table | Load category names/colors from text file | 2025-05-23 | 2025-05-23 | 1
Sprint 2 | Data Entry Table | Add time summation feature | 2025-05-24 | 2025-05-24 | 1
Sprint 2 | Data Entry Table | Add row deletion feature via mouse selection | 2025-05-24 | 2025-05-24 | 1
Sprint 2 | Data Entry Table | Write unit tests | 2025-05-24 | 2025-05-24 | 1
Sprint 3 | Database Setup & Integration | Audit and inventory raw data | 2025-05-26 | 2025-05-26 | 1
Sprint 3 | Database Setup & Integration | Define cleaning and privacy rules | 2025-05-26 | 2025-05-27 | 2
Sprint 3 | Database Setup & Integration | Clean and preprocess data | 2025-05-27 | 2025-05-28 | 2
Sprint 3 | Database Setup & Integration | Design MongoDB schema | 2025-05-28 | 2025-05-28 | 1
Sprint 3 | Database Setup & Integration | Set up MongoDB Atlas cluster | 2025-05-28 | 2025-05-29 | 2
Sprint 3 | Database Setup & Integration | Insert cleaned data | 2025-05-29 | 2025-05-29 | 1
Sprint 3 | Database Setup & Integration | Create indexes for common queries | 2025-05-30 | 2025-05-30 | 1
Sprint 3 | Database Setup & Integration | Write connection instructions for backend | 2025-05-30 | 2025-05-30 | 1
Sprint 3 | Database Setup & Integration | Test access and security | 2025-05-31 | 2025-05-31 | 1
Sprint 3 | Backend Setup | Initialize Flask project structure | 2025-05-26 | 2025-05-26 | 1
Sprint 3 | Backend Setup | Install core dependencies | 2025-05-26 | 2025-05-26 | 1
Sprint 3 | Backend Setup | Load and use environment variables | 2025-05-27 | 2025-05-27 | 1
Sprint 3 | Backend Setup | Connect to MongoDB Atlas | 2025-05-27 | 2025-05-28 | 2
Sprint 3 | Backend Setup | Create CRUD API endpoints | 2025-05-28 | 2025-05-29 | 2
Sprint 3 | Backend Setup | Define data access layer (DAL) | 2025-05-29 | 2025-05-29 | 1
Sprint 3 | Backend Setup | Implement input validation and error handling | 2025-05-30 | 2025-05-30 | 1
Sprint 3 | Backend Setup | Write unit and integration tests | 2025-05-30 | 2025-05-31 | 2
Sprint 3 | Backend Setup | Document the API | 2025-05-31 | 2025-05-31 | 1
Sprint 3 | Backend Setup | Run end-to-end tests w/ live DB | 2025-05-31 | 2025-05-31 | 1