## Slide 1: Sprint #2
Monday 5/19 – Saturday 5/24

## Slide 2: Agenda --- 5/19 Monday (Day #1)
Discuss small logistical progress I made yesterday and what I intend on finishing by the end of today

## Slide 3: Previous Progress
Completed sprint 1 presentation
Uploaded backlog descriptions, standups, retrospective, and sprint documentation to GitHub
Emailed Dr. Raymer for presentation request
Started working on timeline

## Slide 4: Problems & Blockers
React, html, css, tailwind css, ui/shadcn learning curve
Timeline is going to take a long time to make
  Create subtasks for all backlog items (8 left)
  Estimate duration of each subtask
  Assign start/end dates
  Research + implement gantt chart software

## Slide 5: Timeline Issue

## Slide 6: Pending Actions
Create rough timeline including Japan
Give sprint 1 presentation later on today
Complete and grade 1st and 2nd quiz
Implement static UI elements using React, html, tailwind css, JavaScript
Fix figma ui mockup
  Version 1: make consistent + download (extra version)
  Version 2: make consistent + remove status bar + download (mvs version ---- remove impulsive feature)

## Slide 7: Next Steps
Create rough timeline including Japan
Give sprint 1 presentation later on today
Complete and grade 1st and 2nd quiz
Fix figma ui mockup
  Version 1: make consistent + download (extra version)
  Version 2: make consistent + remove status bar + download (mvs version ---- remove impulsive feature)

## Slide 8: Agenda --- 5/20 Tuesday (Day #2)
Review poor understanding of react – show quiz scores
Introduce + review rough timeline
Promise immediate timeline will be created by tomorrow

## Slide 9: Previous Progress
Fixed UI mockups (2 versions)
Took quiz 2 for first time (18/40 = 45%)
Retook quiz 1 (13/15 = 87%)
Finished Rough Timeline

## Slide 10: Rough Timeline

## Slide 11: Problems & Blockers
Need to re-read the react article but head hurts and I have brainfog (more difficult to learn with these conditions)

## Slide 12: Next Steps
Re-read react article for quiz 2
Retake + grade quiz 2
Review missed questions in quiz 1
Write up subtasks for backlog items in next sprint (sprint 3)
Create gantt chart for immediate timeline
  Immediate timeline – subtasks of backlog items in the current sprint and the next sprint

## Slide 13: Agenda --- 5/21 Wed + Thu (Day #3-4)
Discuss timelines created (rough/comprehensive timeline + immediate/detailed timeline)
Finally trying to implement the static ui elements to web page (actually coding)

## Slide 14: Previous Progress
Completed rough and immediate timelines
Finished “Introduction to Solo-scrum” backlog item
  2 items left to go

## Slide 15: Immediate Timeline (Sprints 2 & 3)

## Slide 16: Sprints 2 & 3 Timeline (Untouched)

## Slide 17: Timeline: Sprint 2 Progress

## Slide 18: Problems & Blockers
Still don’t have a strong understanding of React
Timeline is a little tight so it might not work

## Slide 19: Next Steps
Add static ui components to web app
  Table
  Stat cards
  Major feedback section
  Submit button

## Slide 20: Agenda --- 5/24 Saturday (Day #5)
Introduce new backlog item: “Intro to React” (~13 hours work)
Discuss basic web app setup + reiterate over “vibe coding”
Shift in schedule
  New backlog item: work on it this and next sprint
  Finish ui/ux foundation for sprint 2
  Push data entry table to the 4th sprint, move to third if “Intro to React” is finished early
  Japan trip moved to July
Professor meeting on Wednesday
Meeting over zoom

## Slide 21: Previous Progress – Intro to React

## Slide 22: Previous Progress – Static Implementation

## Slide 23: Problems & Blockers
Still wont finish project by July but will get much closer
Might need to pay for codeacademy subscription – not a big problem
There is the potential for me to not know how to implement the data table backlog item even after finishing the “Intro to React” backlog item
Annoying to manually update gantt chart and timeline every time

## Slide 24: Next Steps